## Jan 18
|  | DAILY GEOLOGICAL REPORT | [7 empty] | Date | 1/18/2026
|  | Suncor LS7 11-19-74-12W4 | [7 empty] | Report # |  | 1
|  | 100/11-19-074-12W4/00 | [7 empty] | Days from spud |  | N/A
WELL CONTACTS | [9 empty] | PHONE NUMBERS
Operator | Suncor Energy Inc. |  |  | Office Geologist |  |  | Andres Altosaar |  |  | 403-296-3451
Wellsite Geology Contractor | Chinook Consulting Services |  |  | Wellsite Geologists |  | Days | Nicole Boulton |  |  | 403-461-3232
[6 empty] | Nights | Bob Qin |  |  | 587-580-8512
Drilling Rig | PD 144 |  |  | Drilling Supervisors |  | Days | Craig Hayward |  |  | RIG PHONE #
[6 empty] | Nights | Robert Sterry |  |  | 780-215-1588
WELL DETAILS
License No. | 0521625 |  | Depth @ 06:00 Hrs. (m) |  | 0 |  |  | HOLE GEOMETRY |  | SIZE | DEPTH | MUD
AFE No. | SUENTQ00166572 |  | 24 Hr. Progress |  | 0 |  |  | Surface Hole |  | 311 |  | Gel
Spud Date | N/A |  | Drill time (hrs) |  | 0 |  |  | Surface Casing |  | 224.5 |  | Gel
KB | 4.2 |  | Avg ROP (m/hr) |  | 0 |  |  | Intermediate Hole |  | 222 |  | Polymer
GL | 687.62 |  | Current Formation |  |  |  |  | Intermediate Casing |  | 164 |  | Polymer
KB - GL | 691.82 |  | Target Formation |  | Total Depth |  |  | Main Hole |  | 159 |  | Polymer
CURRENT OPERATIONS @ 06:00 HRS.
Preparing to rig move
24HR OPERATIONS SUMMARY - 06:00 TO 06:00 HRS.
Ground too soft, waiting on rig mats to arrive, trucks arrive at site and continue moving equipment to the new LS7 location, logistics truck unexpectedly spun out and jack knifed the road on the OCR, all units stuck behind waiting for truck to be pulled out of the way. Wait and then to move equipment, install rig mats, move equipment and shacks into position. Wait for daylight to continue move the rig on Sunday after the safety meetings at 7:30am each morning.
24HR OPERATIONS FORECAST
Wait for daylight to continue move the rig on Sunday after the safety meetings at 7:30am each morning. Continue rig move from LS8 to LS7.
FORMATION TOPS AND MARKERS | [9 empty] | MUD RESISTIVITY CHECKS
Formation Top / Marker |  | Prognosed |  |  | Cutting Samples / Lithology |  |  |  |  | Sample Depth (m) | Res (Ω) | Temp (°C)
|  | MD (m) | TVD (M) | TVDASL (m) | MD (m) | TVD (m) | TVDASL (m) | Prog - Sample (m)
Clearwater |  | 418.12 | 418.12 | 273.7
Surface Casing |  | 428.12 | 428.12 | 263.7
BGWP |  | 461.55 | 461.55 | 230.27
McMurray |  | 496.32 | 496.32 | 195.5
SCU |  | 532.82 | 532.82 | 159
Beaverhill Lake |  | 649.2 | 649.2 | 42.62
Slave Point |  | 834.2 | 834.2 | -142.38
Fort Vermillion |  | 838.2 | 838.2 | -146.38
Watt Mountain |  | 859.82 | 859.82 | -168
Prairie Evaporite |  | 868.82 | 868.82 | -177
Shell Lake Mbr |  | 1048.82 | 1048.82 | -357
Intermediate Casing |  | 1048.82 | 1048.82 | -357
Core Point |  | 1048.82 | 1048.82 | -357
Upper Keg River |  | 1055.82 | 1055.82 | -364
Contact Rapids |  | 1105.82 | 1105.82 | -414
Total Depth |  | 1118.82 | 1118.82 | -427
OVERALL CORING DETAILS
Total Core Cut (m) |  | Total Core Recovered (m) |  |  | Total Recovery (%) |  | Coring Start Depth (m) |  | # of Core Runs |  | Total Hours
ADDITIONAL REMARKS
Tentatively spud LS7 on Monday night or Tuesday.

## Jan 19
|  | DAILY GEOLOGICAL REPORT | [7 empty] | Date | 1/19/2026
|  | Suncor LS7 11-19-74-12W4 | [7 empty] | Report # |  | 2
|  | 100/11-19-074-12W4/00 | [7 empty] | Days from spud |  | N/A
WELL CONTACTS | [9 empty] | PHONE NUMBERS
Operator | Suncor Energy Inc. |  |  | Office Geologist |  |  | Andres Altosaar |  |  | 403-296-3451
Wellsite Geology Contractor | Chinook Consulting Services |  |  | Wellsite Geologists |  | Days | Nicole Boulton |  |  | 403-461-3232
[6 empty] | Nights | Bob Qin |  |  | 587-580-8512
Drilling Rig | PD 144 |  |  | Drilling Supervisors |  | Days | Craig Hayward |  |  | RIG PHONE #
[6 empty] | Nights | Robert Sterry |  |  | 780-215-1588
WELL DETAILS
License No. | 0521625 |  | Depth @ 06:00 Hrs. (m) |  | 0 |  |  | HOLE GEOMETRY |  | SIZE | DEPTH | MUD
AFE No. | SUENTQ00166572 |  | 24 Hr. Progress |  | 0 |  |  | Surface Hole |  | 311 |  | Gel
Spud Date | N/A |  | Drill time (hrs) |  | 0 |  |  | Surface Casing |  | 224.5 |  | Gel
KB | 4.2 |  | Avg ROP (m/hr) |  | 0 |  |  | Intermediate Hole |  | 222 |  | Polymer
GL | 687.62 |  | Current Formation |  |  |  |  | Intermediate Casing |  | 164 |  | Polymer
KB - GL | 691.82 |  | Target Formation |  | Total Depth |  |  | Main Hole |  | 159 |  | Polymer
CURRENT OPERATIONS @ 06:00 HRS.
Rigging up
24HR OPERATIONS SUMMARY - 06:00 TO 06:00 HRS.
Wait for daylight to start moving equipment or shacks. Start laying down rig mats, move shacks into position, place equipment and rig it in. Place/setup equipment and rig. Rig up.
24HR OPERATIONS FORECAST
Continue to rig up. Spud well. Drill surface hole.
FORMATION TOPS AND MARKERS | [9 empty] | MUD RESISTIVITY CHECKS
Formation Top / Marker |  | Prognosed |  |  | Cutting Samples / Lithology |  |  |  |  | Sample Depth (m) | Res (Ω) | Temp (°C)
|  | MD (m) | TVD (M) | TVDASL (m) | MD (m) | TVD (m) | TVDASL (m) | Prog - Sample (m)
Clearwater |  | 418.12 | 418.12 | 273.7
Surface Casing |  | 428.12 | 428.12 | 263.7
BGWP |  | 461.55 | 461.55 | 230.27
McMurray |  | 496.32 | 496.32 | 195.5
SCU |  | 532.82 | 532.82 | 159
Beaverhill Lake |  | 649.2 | 649.2 | 42.62
Slave Point |  | 834.2 | 834.2 | -142.38
Fort Vermillion |  | 838.2 | 838.2 | -146.38
Watt Mountain |  | 859.82 | 859.82 | -168
Prairie Evaporite |  | 868.82 | 868.82 | -177
Shell Lake Mbr |  | 1048.82 | 1048.82 | -357
Intermediate Casing |  | 1048.82 | 1048.82 | -357
Core Point |  | 1048.82 | 1048.82 | -357
Upper Keg River |  | 1055.82 | 1055.82 | -364
Contact Rapids |  | 1105.82 | 1105.82 | -414
Total Depth |  | 1118.82 | 1118.82 | -427
OVERALL CORING DETAILS
Total Core Cut (m) |  | Total Core Recovered (m) |  |  | Total Recovery (%) |  | Coring Start Depth (m) |  | # of Core Runs |  | Total Hours
ADDITIONAL REMARKS
Tentatively spud LS7 on Monday night or Tuesday.

## Jan 20
|  | DAILY GEOLOGICAL REPORT | [7 empty] | Date | 1/20/2026
|  | Suncor LS7 11-19-74-12W4 | [7 empty] | Report # |  | 3
|  | 100/11-19-074-12W4/00 | [7 empty] | Days from spud |  | 0
WELL CONTACTS | [9 empty] | PHONE NUMBERS
Operator | Suncor Energy Inc. |  |  | Office Geologist |  |  | Andres Altosaar |  |  | 403-296-3451
Wellsite Geology Contractor | Chinook Consulting Services |  |  | Wellsite Geologists |  | Days | Nicole Boulton |  |  | 403-461-3232
[6 empty] | Nights | Bob Qin |  |  | 587-580-8512
Drilling Rig | PD 144 |  |  | Drilling Supervisors |  | Days | Craig Hayward |  |  | RIG PHONE #
[6 empty] | Nights | Robert Sterry |  |  | 780-215-1588
WELL DETAILS
License No. | 0521625 |  | Depth @ 06:00 Hrs. (m) |  | 150 |  |  | HOLE GEOMETRY |  | SIZE | DEPTH | MUD
AFE No. | SUENTQ00166572 |  | 24 Hr. Progress |  | 150 |  |  | Surface Hole |  | 311 |  | Gel
Spud Date | 2026-01-20 |  | Drill time (hrs) |  | 5 |  |  | Surface Casing |  | 224.5 |  | Gel
KB | 4.76 |  | Avg ROP (m/hr) |  | 30 |  |  | Intermediate Hole |  | 222 |  | Polymer
GL | 687.18 |  | Current Formation |  |  |  |  | Intermediate Casing |  | 164 |  | Polymer
KB - GL | 691.94 |  | Target Formation |  | Total Depth |  |  | Main Hole |  | 159 |  | Polymer
CURRENT OPERATIONS @ 06:00 HRS.
Drilling
24HR OPERATIONS SUMMARY - 06:00 TO 06:00 HRS.
Continued to rig up/ level off walkways/ stairways, and equipment, spot buildings, fill in holes on mats, rig up flare and degasser, build volume, and wait on water. Make sure the site is cleaned up, all debris removed, everything is rigged in, and ready to spud. Pick up 311mm BHA, Pre-spud hazard hunt and safety meeting. Spud well, drill 311mm surface hole to 150m.
24HR OPERATIONS FORECAST
Continue to drill surface hole to surface casing point. Condition mud & circulate. POOH. Laydown 311mm BHA. Run surface casing. Cement casing. WOC.
FORMATION TOPS AND MARKERS | [9 empty] | MUD RESISTIVITY CHECKS
Formation Top / Marker |  | Prognosed |  |  | Cutting Samples / Lithology |  |  |  |  | Sample Depth (m) | Res (Ω) | Temp (°C)
|  | MD (m) | TVD (M) | TVDASL (m) | MD (m) | TVD (m) | TVDASL (m) | Prog - Sample (m)
Clearwater |  | 418.24 | 418.24 | 273.7
Surface Casing |  | 428.24 | 428.24 | 263.7
BGWP |  | 461.67 | 461.67 | 230.27
McMurray |  | 496.44 | 496.44 | 195.5
SCU |  | 532.94 | 532.94 | 159
Beaverhill Lake |  | 649.32 | 649.32 | 42.62
Slave Point |  | 834.32 | 834.32 | -142.38
Fort Vermillion |  | 838.32 | 838.32 | -146.38
Watt Mountain |  | 859.94 | 859.94 | -168
Prairie Evaporite |  | 868.94 | 868.94 | -177
Shell Lake Mbr |  | 1048.94 | 1048.94 | -357
Intermediate Casing |  | 1048.94 | 1048.94 | -357
Core Point |  | 1048.94 | 1048.94 | -357
Upper Keg River |  | 1055.94 | 1055.94 | -364
Contact Rapids |  | 1105.94 | 1105.94 | -414
Total Depth |  | 1118.94 | 1118.94 | -427
OVERALL CORING DETAILS
Total Core Cut (m) |  | Total Core Recovered (m) |  |  | Total Recovery (%) |  | Coring Start Depth (m) |  | # of Core Runs |  | Total Hours
ADDITIONAL REMARKS

## Jan 21
|  | DAILY GEOLOGICAL REPORT | [7 empty] | Date | 1/21/2026
|  | Suncor LS7 11-19-74-12W4 | [7 empty] | Report # |  | 4
|  | 100/11-19-074-12W4/00 | [7 empty] | Days from spud |  | 1
WELL CONTACTS | [9 empty] | PHONE NUMBERS
Operator | Suncor Energy Inc. |  |  | Office Geologist |  |  | Andres Altosaar |  |  | 403-296-3451
Wellsite Geology Contractor | Chinook Consulting Services |  |  | Wellsite Geologists |  | Days | Nicole Boulton |  |  | 403-461-3232
[6 empty] | Nights | Bob Qin |  |  | 587-580-8512
Drilling Rig | PD 144 |  |  | Drilling Supervisors |  | Days | Craig Hayward |  |  | RIG PHONE #
[6 empty] | Nights | Robert Sterry |  |  | 780-215-1588
WELL DETAILS
License No. | 0521625 |  | Depth @ 06:00 Hrs. (m) |  | 427 |  |  | HOLE GEOMETRY |  | SIZE | DEPTH | MUD
AFE No. | SUENTQ00166572 |  | 24 Hr. Progress |  | 277 |  |  | Surface Hole |  | 311 | 427 | Gel
Spud Date | 2026-01-20 |  | Drill time (hrs) |  | 7 |  |  | Surface Casing |  | 224.5 |  | Gel
KB | 4.76 |  | Avg ROP (m/hr) |  | 39.6 |  |  | Intermediate Hole |  | 222 |  | Polymer
GL | 687.18 |  | Current Formation |  | Surface Casing |  |  | Intermediate Casing |  | 164 |  | Polymer
KB - GL | 691.94 |  | Target Formation |  | Total Depth |  |  | Main Hole |  | 159 |  | Polymer
CURRENT OPERATIONS @ 06:00 HRS.
Running casing
24HR OPERATIONS SUMMARY - 06:00 TO 06:00 HRS.
Drill 311mm surface hole from 150mKB to 388mKB. Continue to drill surface hole to surface casing point 427mKB. Condition mud & circulate. TOOH, lay down BHA, run surface casing, rig in cementers, cement casing, w/o cement.
24HR OPERATIONS FORECAST
Continue to run surface casing, rig in cementers, cement casing, w/o cement.
FORMATION TOPS AND MARKERS | [9 empty] | MUD RESISTIVITY CHECKS
Formation Top / Marker |  | Prognosed |  |  | Cutting Samples / Lithology |  |  |  |  | Sample Depth (m) | Res (Ω) | Temp (°C)
|  | MD (m) | TVD (M) | TVDASL (m) | MD (m) | TVD (m) | TVDASL (m) | Prog - Sample (m)
Clearwater |  | 418.24 | 418.24 | 273.7 | 410 | 410 | -405.24 | 8.24
Surface Casing |  | 428.24 | 428.24 | 263.7 | 427 | 427 | -422.24 | 1.24
BGWP |  | 461.67 | 461.67 | 230.27
McMurray |  | 496.44 | 496.44 | 195.5
SCU |  | 532.94 | 532.94 | 159
Beaverhill Lake |  | 649.74 | 649.74 | 42.2
Slave Point |  | 834.74 | 834.74 | -142.8
Fort Vermillion |  | 838.74 | 838.74 | -146.8
Watt Mountain |  | 859.94 | 859.94 | -168
Prairie Evaporite |  | 868.94 | 868.94 | -177
Shell Lake Mbr |  | 1048.94 | 1048.94 | -357
Intermediate Casing |  | 1048.94 | 1048.94 | -357
Core Point |  | 1048.94 | 1048.94 | -357
Upper Keg River |  | 1055.94 | 1055.94 | -364
Contact Rapids |  | 1105.94 | 1105.94 | -414
Total Depth |  | 1118.94 | 1118.94 | -427
OVERALL CORING DETAILS
Total Core Cut (m) |  | Total Core Recovered (m) |  |  | Total Recovery (%) |  | Coring Start Depth (m) |  | # of Core Runs |  | Total Hours
ADDITIONAL REMARKS

## Jan 22
|  | DAILY GEOLOGICAL REPORT | [7 empty] | Date | 1/22/2026
|  | Suncor LS7 11-19-74-12W4 | [7 empty] | Report # |  | 5
|  | 100/11-19-074-12W4/00 | [7 empty] | Days from spud |  | 2
WELL CONTACTS | [9 empty] | PHONE NUMBERS
Operator | Suncor Energy Inc. |  |  | Office Geologist |  |  | Andres Altosaar |  |  | 403-296-3451
Wellsite Geology Contractor | Chinook Consulting Services |  |  | Wellsite Geologists |  | Days | Nicole Boulton |  |  | 403-461-3232
[6 empty] | Nights | Bob Qin |  |  | 587-580-8512
Drilling Rig | PD 144 |  |  | Drilling Supervisors |  | Days | Craig Hayward |  |  | RIG PHONE #
[6 empty] | Nights | Robert Sterry |  |  | 780-215-1588
WELL DETAILS
License No. | 0521625 |  | Depth @ 06:00 Hrs. (m) |  | 427 |  |  | HOLE GEOMETRY |  | SIZE | DEPTH | MUD
AFE No. | SUENTQ00166572 |  | 24 Hr. Progress |  | 0 |  |  | Surface Hole |  | 311 | 427 | Gel
Spud Date | 2026-01-20 |  | Drill time (hrs) |  | 0 |  |  | Surface Casing |  | 224.5 | 427 | Gel
KB | 4.76 |  | Avg ROP (m/hr) |  | 0 |  |  | Intermediate Hole |  | 222 |  | Polymer
GL | 687.18 |  | Current Formation |  | BGWP |  |  | Intermediate Casing |  | 164 |  | Polymer
KB - GL | 691.94 |  | Target Formation |  | Total Depth |  |  | Main Hole |  | 159 |  | Polymer
CURRENT OPERATIONS @ 06:00 HRS.
RIH
24HR OPERATIONS SUMMARY - 06:00 TO 06:00 HRS.
Continued to run casing, condition mud and circulate, rig in cementers, pump cement, plug down, bump plug, rig out cementers,w/o cement, cut casing, and weld on the bowl, nipple up BOPs. Pressure/ function test, M/U & P/U BHA, RIH.
24HR OPERATIONS FORECAST
Continue to RIH, tag cement, drill out cement and plug, continue to drill intermediate section to ICP. Condition mud and circulate. Wiper trip.
FORMATION TOPS AND MARKERS | [9 empty] | MUD RESISTIVITY CHECKS
Formation Top / Marker |  | Prognosed |  |  | Cutting Samples / Lithology |  |  |  |  | Sample Depth (m) | Res (Ω) | Temp (°C)
|  | MD (m) | TVD (M) | TVDASL (m) | MD (m) | TVD (m) | TVDASL (m) | Prog - Sample (m)
Clearwater |  | 418.24 | 418.24 | 273.7 | 410 | 410 | -405.24 | 8.24
Surface Casing |  | 428.24 | 428.24 | 263.7 | 427 | 427 | -422.24 | 1.24
BGWP |  | 461.67 | 461.67 | 230.27
McMurray |  | 496.44 | 496.44 | 195.5
SCU |  | 532.94 | 532.94 | 159
Beaverhill Lake |  | 649.74 | 649.74 | 42.2
Slave Point |  | 834.74 | 834.74 | -142.8
Fort Vermillion |  | 838.74 | 838.74 | -146.8
Watt Mountain |  | 859.94 | 859.94 | -168
Prairie Evaporite |  | 868.94 | 868.94 | -177
Shell Lake Mbr |  | 1048.94 | 1048.94 | -357
Intermediate Casing |  | 1048.94 | 1048.94 | -357
Core Point |  | 1048.94 | 1048.94 | -357
Upper Keg River |  | 1055.94 | 1055.94 | -364
Contact Rapids |  | 1105.94 | 1105.94 | -414
Total Depth |  | 1118.94 | 1118.94 | -427
OVERALL CORING DETAILS
Total Core Cut (m) |  | Total Core Recovered (m) |  |  | Total Recovery (%) |  | Coring Start Depth (m) |  | # of Core Runs |  | Total Hours
ADDITIONAL REMARKS

## Date
|  | DAILY GEOLOGICAL REPORT | [7 empty] | Date
Report #
Days from spud
WELL CONTACTS | [9 empty] | PHONE NUMBERS
Operator | Suncor Energy Inc. |  |  | Office Geologist
Wellsite Geology Contractor | Chinook Consulting Services |  |  | Wellsite Geologists |  | Days
Nights
Drilling Rig |  |  |  | Drilling Supervisors |  | Days |  |  |  | RIG PHONE #
Nights
WELL DETAILS
License No. |  |  | Depth @ 06:00 Hrs. (m) |  |  |  |  | HOLE GEOMETRY |  | SIZE | DEPTH | MUD
AFE No. |  |  | 24 Hr. Progress |  |  |  |  | Surface Hole
Spud Date |  |  | Drill time (hrs) |  |  |  |  | Surface Casing
KB |  |  | Avg ROP (m/hr) |  |  |  |  | Intermediate Hole
GL |  |  | Current Formation |  |  |  |  | Intermediate Casing
KB - GL |  |  | Target Formation |  |  |  |  | Main Hole
CURRENT OPERATIONS @ 06:00 HRS.
24HR OPERATIONS SUMMARY - 06:00 TO 06:00 HRS.
24HR OPERATIONS FORECAST
FORMATION TOPS AND MARKERS | [9 empty] | MUD RESISTIVITY CHECKS
Formation Top / Marker |  | Prognosed |  |  | Cutting Samples / Lithology |  |  |  |  | Sample Depth (m) | Res (Ω) | Temp (°C)
|  | MD (m) | TVD (M) | TVDASL (m) | MD (m) | TVD (m) | TVDASL (m) | Prog - Sample (m)
OVERALL CORING DETAILS
Total Core Cut (m) |  | Total Core Recovered (m) |  |  | Total Recovery (%) |  | Coring Start Depth (m) |  | # of Core Runs |  | Total Hours
ADDITIONAL REMARKS